## Member list 2024-25
UN Nepal Common Services - Human Resource Working Group - Members 2024
S.N | Name | Agency | Designation in working group (Chair/member/Alternate member) | S.N | Name | Agency | Designation in working group (Chair/member/Alternate member)
1 | Durga Kumari Lohar | RCO | Member | 15 | Isha Dhaubhadel | UNFPA | Member
2 | Sunita Pradhan | UN HABITAT | Coordinator | 16 | Dhruba Aryal | UNFPA | Alternate Member
3 | Lhawang Lama | UN-WOMEN | Deputy Coordinator | 17 | Dipesh Sherchan | WHO | Member
4 | Dhan Bahadur Shrestha | FAO | Member | 18 | Ruby Bajracharya | WHO | Alternate Member
5 | Bhakta Ram Baral | FAO | Alternate | 19 | Mala Rai | WFP | Member
6 | Rina Chhetri | UNDP | Member | 20 | Sujan Pradhan | WFP | Alternate Member
7 | Ira Mishra | UNDP | Alternate | 21 | Nandita RAI | WFP | Alternate member
8 | Marina Rai | ILO | Member | 22 | Kamana Shrama Pandit | UNHCR | Member
9 | Deepika Chhetri | UNICEF | Member | 23 | Uma Basnet | UNHCR | Alternate member
10 | Babita Das | UNICEF | Alternate Member | 24 | Shrijana Maharjan | UNOPS | Member
11 | Arisha Gurung | UNICEF ROSA | Member | 25 | Rita Rana | IOM | Member
12 | Glory Sodemba | UNICEF ROSA | Alternate Member | 26 | Pishan Giri | IOM | Alternate member
13 | Gomba Sherpa | UNESCO | Member | 27 | Aruna Shrsetha | UNRCPD | Member
14 | Richa Shrestha | UNESCO | Alternate Member | 28 | Rina Pradhan | UNV | Alternate member
|  |  |  | 29 | Krishna Prasad Sedhain | UNODC | Member

## Challenges
UN Nepal Common Services - OMT work-plan 2024- Progreess as of 31 March 2024
S. No. | Output Categories | S.N for Activities | Activities | S.N for sub-activities | Sub- Activities | Indicators | Baseline data 2023 | Target | Cost USD | Timeline |  | CBA | Lead agency | Remarks | Progress as of 31October 2024 | Key Challenges
Inter Agency HR Working Group (IAHRWG)
1 | Benefit Administration | 1.1 | Benefit Management | 1.1.1 | UN DSA Survey-Regular DSA survey to keep the DSA rate up-to-date. | UN staff are compensate as per the prevailing market rates | 1 | 1 | 0 | 2024-01-01 | 2024-10-01 | NO |  | Activity supported by UN Habitat. To be consulted with Finance | HRWG supported to collect hotel list and FWG is working . Data Entry in the ICSC Protal
|  | 1.2 | Knowledge Sharing | 1.2.1 | Online General Information session to UN personnel on BOS by BOS team HQ | UN personnel sensitized on BOS | 0 | 1 | 0 | 2024-05-01 | 2024-05-01 | NO | ILO | Activity supported by UN Habitat
2 |  |  |  | 1.2.3 | Information on medical plan/services (CIGNA) | Enhance entitlement benefit awareness among staff. | 1 | 2 | 0 | January and March 2024 | Jan to June 2024 | NO | UNDP |  | UNDP organized Orientation on 18 on FTA /TA and 23 January 2024 to the personnel under NPSA/SC those are UNDP's administration .Facilitator was by Ms. Vanessa Vermeulen, CIGNA CIGNA Training provided to all FTA staff on 6 May and for SC on 3rd June
3 | Recruitment Services | 2.1 | Gender Parity | 2.1.1 | Conduct job fairs to raise awareness and attract female candidates considering GESI | Special measure put in place by agencies for achieving 50% women WD in UN Agencies as well as inclusion of Marginalized group .Ensure GESI guideline is followed by agencies | 2 | 1 | 2000 | 2024-07-01 | 2024-08-01 | NO | UNICEF | WHO, WFP, UNDP, UNV to support | Complted -Job Fair Conducted on 17 July 2024 at UN House , Pulchowk . 70 In persons Participants and 135 on-line Participants for Job Career session and 450 participants in Exhibition . Report with annexces shared to OMT Participated in Job Fair organized by Ministry of Labor, Employment and Security facilitated by FNCCI on 11th and 12th June 2024(UN Habitat, UNFPA, UNICEF, WFP, UNDP, IOM, ILO, UN Women, UNV, UNHCR, UNV) | Overwhelming applications received for participation, hence the online registration was closed before closing date. Participation of limited targeted group Finalization of venue for the event was challenging, cooperation from OMT Co-Chair to allocate UN House led to success of the event. Good Thing: Collaboration from participation of HR colleagues of UN agencies under the leadership of UNV led to success of the event Lessons learnt: Outreach to potential target group Multiple sessions can be done
4 |  |  |  | 2.1.2 | Maintain job Roster of female drivers /marginalized people | Roster of female driver created | 2 | 4 | 0 | 2024-12-01 | 2024-12-01 | NO | UN WOMEN | WFP/UNDP to support; Submit concept note incorporating best practices and challenges to OMT for further decision | Presented concept note with best practices to the OMT the Women on Wheel ( WFP /UNWOMEN) projects to OMT to initiate UN Joint activities as per the requested by OMT Concept note with cost was submitted to OMT (meeting conducted in WHO) and is still pending for OMT approval
5 |  |  |  | 2.1.3 | Establish GESI policy by agencies and policy Enhancement |  | 8 | 15 | 0 | 2024-12-01 | 2024-12-01 | NO | UNDP | UNHABITAT to support; GESI policy mapping survey on current status and report to OMT for further decision | UNDP hired consultant to finalize GESI policy. Mapping will be done within this year 2024 | Some agencies don't have their GESI policy GESI policy developed by one agency cannot be adopted by another agency due to their own agency global policy
5 |  | 2.2 | Gender Equality and Social Inclusion in UN Workforce in Nepal. | 2.2.1 | 1. Quarterly basis GESI data presented to OMT and UNCT . 2. Conduct joint workshop with participation from HRWG, OMT, UNCT and LNOB WG on lesson learning and Way forward . | Number of agencies achieve above Gender Parity ; Lesson Learnt and action point developed; | 4 | 7 | 0 | Quarterly update | Quarterly update | NO | UN WOMEN | Survey, mapping, report and strategy; Implement in 2025 after endorsement by RC | Data as of 31 March 2024 and best Practices collected and compiled from all agencies. Best practives will be presented in the next OMT meeting | GESI data is collected, compiled and presented on quarterly basis to OMT and UNCT. UNCT level commitment is required to improve agency wise.
|  | 2.3 | Integrated Web-base Roster for Staff | 2.3.1 | Established web based roster for staff/personnel in DCO UN website | Reduce the lead time for recruitment process, save cost and fast track recruitment process. (number of CVs available in the webpage) | 46 | 75 | 0 | 2024-12-01 | 2024-12-01 | Simplified CBA | UNFPA |  | Completed
|  |  | UN Personnel Job security | 2.3.2 | Maintain roster of potential candidates in UN website to facilitate recruitment of personnel in the UN agencies | Number of UN personnel hired from the roster and number of UN personnel retained. | 0 | 5 | 0 | 2024-12-01 | 2024-12-01 |  | UNFPA |  | Some agencies are uploading profiles. | Respective agency HR has to prioritize
|  | 2.4 | Joint Recruitment Panel | 2.4.1 | Engage Staff members across UN agencies for various recruitment activities i.e. shortlisting , written test evaluation and interviews. | Cross utilization of expertise , recruitment of qualified personnel and cost saving by using internal resources. | 19 | 25 | 0 | Quarterly update | Quarterly update | NO | WFP |  | In progress
|  | 2.5 | Use Outsource company/consultant | 2.5.1 | Outsource company/consultant to be used for long listing and to conduct written tests in various recruitment process | Fast track recruitment process. Cost saving through the use of common agency in terms of human resource and time and efficient services. | 4 | 4 | 0 | 2024-12-01 | 2024-12-01 | LTA CBA | UNDP |  | UNDP, UN Habitat, WFP Reduced due to policies of individual agencies | Encourage UN agencies to utilize services of outsource companies/Individuals for cost efficiency. Support expected from OM level.
6 |  | 2.6 | Harmonization in induction package. | 2.6.1 | Update and distribution of Common UN induction package to for all agencies | Updated induction package for all agencies | 1 | 1 | 0 | 2024-03-01 | 2024-03-01 | NO | UNICEF | Each agency will provide information by March in 2023 | Achieved | Delayed in reviewing and providing clearance for the induction package
7 |  | 2.7 | Traineeship Programme for Socially Excluded Group | 2.7.1 | UN Nepal Joint Traineeship Programme to enhance capacity of socially excluded groups to join the UN workforce and others. Cohort X initiated | Increase number of participating agencies to promote the Programme and capacitate more people from marginalized groups. | 0 | 30 | 0 | 2024-03-01 | 2024-03-01 | NO | UNDP | Traineeship initiated in 2023; Will take forward in 2024; Tentatively onboard on March 2024 | 5 agencies ( UNDP, UNWOMEN, UNFPA and UNICEF) are participated . Only 34 trainees for Cohort X where as 9 agencies were in IX cohort with 65 Trainees. Survey has been done to map the know the effectiveness and way of expansion it | Decreasing number of agencies participating in traineeship. Hence, commitment from UNCT level required. Survey completed by HR on traineeship programme which will be shared with OMT. HRWG proposes to provide orientation to UNCT on the programme.
8 | Staff Wellbeing | 3.1 | PSEA - Prevention of Sexual Exploitation and Abuse and Sexual Harassment | 3.1.1 | Support for the PSEA Working Group in conducting the PSEA and SH induction or refresher sessions for all UN personnel, as well as adherence to the PSEA and SH standards of conduct. | Harassment and exploitation free environment among staff and office . Monitoring through monkey survey | 1 | 1 | 0 | 2024-12-31 | 2024-12-01 | NO | UN Habitat | UN-Women, RCO to support. Monkey survey report to be presented (Support to PSEA Coordinator as required); Baseline data will be provided later | Completed - Survey has been done and shared to OMT on 23 September 2024 .
9 |  |  |  | 3.1.2 | Include PSEA in the performance appraisal of the Agency PSEA Focal Points | PSEA is one of the priority areas of PSEA Focal in PMD or performance appraisal |  |  | 0 | 2024-12-01 | 2024-12-01 | NO | All Agencies
|  | 3.3 | UN care and UN day | 3.3.1 | Support UN Care activities for UN staff and dependents, including yearly celebration of UN Day. And update to HRWG on the UN care activities | Update on the UN care and UN day Activities to HRWG/OMT through of chair | 1 | 0 | 0 | May and June 2024 | May and June 2024 | NO | UNIC | After consultation with UN Care
4 | Training and Capacity Building | 4.1 | Follow up session on Disability Inclusion | 4.1.1 | Follow-up session on Disability Inclusive HR based on training of 2022 and implementation of joint actions and lessons identified in 2022. | Disability friendly environment and HR processes in the office | 0 | 1 | 1000 | 2024-04-01 | 2024-04-01 | NO | UN Habitat | RCO to be consulted ; Hire consultant to review action point taken by the agencies and further follow up session and report | will initiate
|  | 4.2 | Implementation of Disability Inclusion Pilot project | 4.2.1 | Implementation of the Global Partnership on Disability Inclusion Pilot -HR components (detailed work plan separately) | [6 empty] | NO | RCO | To be done after consultation with RCO
|  | 4.3 | Training for HR working group (need to identify) | 4.3.1 | Training to HR WG | Artificial Intelligence in HR | 0 | 1 | 1000 | 2024-08-23 | 2024-08-01 | Simplified CBA | UNV | , UNDP, UN-Habitat, UN-Women to support | will initiate
[6 empty] | Total Budget for IAHRWG |  |  | 4000

## Total Budget
Activities | Budget USD | Expenses USD | Balance USD | Remarks
Conduct job fairs to raise awareness and attract female candidates considering GESI | 2000 | 2075 | -75
Follow up session on Disability Inclusion | 1000 | 0 | 1000
Training for HR WG | 1000 | 0 | 1000
Total | 4000 | - | 1925
48.12%

## Attendance
UN Nepal Common Services - Human Resource Working Group - Members
S.N | Name | Designation in working group (Chair/member/Alternate member) | Attendance 25 March 2024 meeting- UN-Habitat | Meeting for Job Fair ( July to mid-August 2024) - 8 meetings | Online Meeting for ToR - DI Conultant on 23 September 2024
1 | Durga Kumari Lohar | Member |  |  | yes
2 | Sunita Pradhan | Coordinator | yes | Yes | yes
3 | Lhawang Lama | Deputy Coordinator | yes | Yes | yes
4 | Dhan Bahadur Shrestha | Member
5 | Bhakta Ram Baral | Alternate |  |  | yes
6 | Rina Chhetri | Member | yes | Yes | yes
7 | Ira Mishra | Alternate |  | Yes
8 | Marina Rai | Member |  | Yes
9 | Deepika Chhetri | Member | yes | Yes
10 | Babita Das | Alternate Member | yes | Yes
11 | Arisha Gurung | Member
12 | Glory Sodemba | Alternate Member
13 | Gomba Sherpa | Member | yes | Yes
14 | Richa Shrestha | Alternate Member
15 | Isha Dhaubhadel | Member | yes | Yes
| Dhruba Aryal | Alternate Member
16 | Dipesh Sherchan | Member |  | YEs
17 | Mala Rai | Member | yes | Yes
18 | Sujan Prdhan | Alternate Member
19 | Nandita RAI | Alternate member
20 | Kamana Shrama Pandit | Member |  | YEs
21 | Uma Basnet | Alternate member
22 | Shrijana Maharjan | Member | yes | Yes | yes
23 | Rita Rana | Member |  | Yes | yes
24 | Pishan Giri | Alternate member |  | Yes
25 | Aruna Shrsetha | Member |  | Yes
26 | Suran Maharjan/Rina Pradhan | Alternate member |  | Yes
27 | Krishna Prasad Sedhain | Member |  |  | yes
|  |  | 9 | 17 | 8

## Work-plan 2024
UN Nepal Common Services - OMT work-plan 2024
S. No. | Output Categories | S.N for Activities | Activities | S.N for sub-activities | Sub- Activities | Indicators | Baseline data 2023 | Target | Cost USD | Timeline |  | CBA | Lead agency | Remarks | Progress as of 31 May 2024 | Lesson Learnt/Note
Inter Agency HR Working Group (IAHRWG)
1 | Benefit Administration | 1.1 | Benefit Management | 1.1.1 | UN DSA Survey-Regular DSA survey to keep the DSA rate up-to-date. | UN staff are compensate as per the prevailing market rates | 1 | 1 | 0 | 2024-01-01 | 2024-10-01 | NO | UN-Habitat | Activity supported by UN Habitat. To be consulted with Finance | HRWG supported to collect hotel list and FWG is working . Data Entry in the ICSC Protal |  | BOS
|  | 1.2 | Knowledge Sharing | 1.2.1 | Online General Information session to UN personnel on BOS by BOS team HQ | UN personnel sensitized on BOS | 0 | 1 | 0 | 2024-11-01 | 2024-11-01 | NO | ILO | Activity supported by UN Habitat | Will be initiated for November 2024 |  | BOS
|  |  |  | 1.2.3 | Information on medical plan/services (CIGNA) | Enhance entitlement benefit awareness among staff. | 1 | 2 | 0 | January and March 2024 | Jan-March 2024 | NO | UNDP | Completed | UNDP organized Orientation on 18 on FTA /TA and 23 January 2024 to the personnel under NPSA/SC those are UNDP's administration .Facilitator was by Ms. Vanessa Vermeulen, CIGNA CIGNA Training provided to all FTA staff on 6 May and for SC on 3rd June
2 | Recruitment Services | 2.1 | Gender Parity | 2.1.1 | Conduct job fairs to raise awareness and attract female candidates considering GESI | Special measure put in place by agencies for achieving 50% women WD in UN Agencies as well as inclusion of Marginalized group .Ensure GESI guideline is followed by agencies | 2 | 1 | 2000 | 2024-07-01 | 2024-08-17 | NO | UNV | UNWOMEN, UNICEF, UNDP, UNFPA, UN-HABITTA | Completed -Job Fair Conducted on 17 July 2024 at UN House , Pulchowk . 70 In persons Participants and 135 on-line Participants for Job Career session and 450 participants in Exhibition . Report with annexces shared to OMT | 1. People are not aware of what to see in TOR/JD 2. Huge application was received so we had to control receiving application
Participated in Job Fair organized by Ministry of Labor, Employment and Security facilitated by FNCCI on 11th and 12th June 2024(UN Habitat, UNFPA, UNICEF, WFP, UNDP, IOM, ILO, UN Women, UNV, UNHCR, UNV)
|  |  |  | 2.1.2 | Maintain job Roster of female drivers /marginalized people | Roster of female driver created | 2 | 4 | 0 | 2024-12-01 | 2024-12-01 | NO | UN WOMEN | WFP/UNDP to support; Submit concept note incorporating best practices and challenges to OMT for further decision | Presented concept note with best practices to the OMT the Women on Wheel ( WFP /UNWOMEN) projects to OMT to initiate UN Joint activities as per the requested by OMT | Concept note with cost was submitted to OMT (meeting conducted in WHO) and request OMT to further approval to take necessary action. Aciviti will be started in 2025
|  |  |  | 2.1.3 | Establish GESI policy by agencies and policy Enhancement |  | 8 | 15 | 0 | 2024-12-01 | 2024-12-01 | NO | UNDP | UNHABITAT to support; GESI policy mapping survey on current status and report to OMT for further decision | UNDP hired consultant to finalize GESI policy. Mapping will be done within this year 2024
|  | 2.2 | Gender Equality and Social Inclusion in UN Workforce in Nepal. | 2.2.1 | 1. Quarterly basis GESI data presented to OMT and UNCT . 2. Conduct joint workshop with participation from HRWG, OMT, UNCT and LNOB WG on lesson learning and Way forward . | Number of agencies achieve above Gender Parity ; Lesson Learnt and action point developed; | 4 | 7 | 0 | Quarterly update | Quarterly update | NO | UN WOMEN | Survey, mapping, report and strategy; Implement in 2025 after endorsement by RC | as per the data as of 31 March IOM 50%, RCO- 55%, Un Women- 69%, UNHCR-48%, Unicef ROSA 59% UNRCPD 56% ( Parity range is 47 to 53%) . 6 Agencies are met GP. | UNCT Focal person should be appointed to monitor and achieve the gender parity Baseline - 47% :53%
[13 empty] | UNWOMEN.ILO, UNHABITAT, UN Secretariat |  | Completed Gemder Score Card on Organizational and cultural Survey for 2024
|  | 2.3 | Integrated Web-base Roster for Staff | 2.3.1 | Established web based roster for staff/personnel in DCO UN website | Reduce the lead time for recruitment process, save cost and fast track recruitment process. (number of CVs available in the webpage) | 46 | 75 | 0 | 2024-12-01 | 2024-12-01 | Simplified CBA | UNFPA |  | Will present | Half day session to be held to upload CVs on 19 November 2024
|  |  | UN Personnel Job security | 2.3.2 | Maintain roster of potential candidates in UN website to facilitate recruitment of personnel in the UN agencies | Number of UN personnel hired from the roster and number of UN personnel retained. | 0 | 5 | 0 | 2024-12-01 | 2024-12-01 |  | UNFPA |  | No report hire from the Roster | Need HR Staff initiation
|  | 2.4 | Joint Recruitment Panel | 2.4.1 | Engage Staff members across UN agencies for various recruitment activities i.e. shortlisting , written test evaluation and interviews. | Cross utilization of expertise , recruitment of qualified personnel and cost saving by using internal resources. | 19 | 25 | 0 | Quarterly update | Quarterly update | NO | UNODC |  | Will present | Ongoing | BOS
|  | 2.5 | Use Outsource company/consultant | 2.5.1 | Outsource company/consultant to be used for long listing and to conduct written tests in various recruitment process | Fast track recruitment process. Cost saving through the use of common agency in terms of human resource and time and efficient services. | 4 | 4 | 0 | 2024-12-01 | 2024-12-01 | LTA CBA | UNDP |  | Outsources Company has been used by UNDP, UN-Habitat, UN WFP | Need OM Commitment to use . Not Included in BOS as only UNDP is using in 2022. Need to OMT Decesion in Include in BOS
|  | 2.6 | Harmonization in induction package. | 2.6.1 | Update and distribution of Common UN induction package to for all agencies | Updated induction package for all agencies | 1 | 1 | 0 | 2024-03-01 | 2024-09-23 | NO | UNICEF |  | Completed. Shared to OMT on 23 September 2024 | Completed delayed in reviewing and providing clearance for the induction package
|  | 2.7 | Traineeship Programme for Socially Excluded Group | 2.7.1 | UN Nepal Joint Traineeship Programme to enhance capacity of socially excluded groups to join the UN workforce and others. Cohort X initiated | Increase number of participating agencies to promote the Programme and capacitate more people from marginalized groups. | 0 | 30 | 0 | 2024-03-01 | 2024-03-01 | NO | UNDP |  | 4 agencies ( UNDP, UNWOMEN, UNFPA and UNICEF) are participating . Only 34 trainees for Cohort X where as 9 agencies were in IX cohort with 65 Trainees. Survey has been done to map to know the effectiveness and way of expansion it | 34 trainees onboard for cohort X Survey on traineeship results will be shared in upcoming OMT meeting Commitment from UNCT level required
3 | Staff Wellbeing | 3.1 | PSEA - Prevention of Sexual Exploitation and Abuse and Sexual Harassment | 3.1.1 | Support for the PSEA Working Group in conducting the PSEA and SH induction or refresher sessions for all UN personnel, as well as adherence to the PSEA and SH standards of conduct. | Harassment and exploitation free environment among staff and office . Monitoring through monkey survey | 1 | 1 | 0 | 2024-12-31 | 2024-12-01 | NO | UN Habitat |  | Completed - Survey has been done and shared to OMT on 23 September 2024 . | Completed
|  |  |  | 3.1.2 | Include PSEA in the performance appraisal of the Agency PSEA Focal Points | PSEA is one of the priority areas of PSEA Focal in PMD or performance appraisal |  |  | 0 | 2024-12-01 | 2024-12-01 | NO | All Agencies, PSEA Coordinator, RCO |  | Completed - Survey has been done and shared to OMT on 23 September 2024 .
|  | 3.3 | UN care and UN day | 3.3.1 | Support UN Care activities for UN staff and dependents, including yearly celebration of UN Day. And update to HRWG on the UN care activities | Update on the UN care and UN day Activities to HRWG/OMT through of chair | 1 | 1 | 0 | May and June 2024 | May and June 2024 | NO | UNIC | After consultation with UN Care | Conducted 1 event on the international day against homophobia, Transphobia and biphobia on 17 May 2024
4 | Training and Capacity Building | 4.1 | Follow up session on Disability Inclusion | 4.1.1 | Follow-up session on Disability Inclusive HR based on training of 2022 and implementation of joint actions and lessons identified in 2022. | Disability friendly environment and HR processes in the office | 0 | 1 | 1000 | 2024-10-01 | 2024-10-01 | NO | UN Habitat | RCO to be consulted ; Hire consultant to review action point taken by the agencies and further follow up session and report | TOR for consultant is finalized with coordinating RCO,LNOB and HRWG team | cost estimation is USD 15,000. For 2024, 30% required and remaining for 2025 . Required additional Fund USD 6000 for this year
|  | 4.2 | Implementation of Disability Inclusion Pilot project | 4.2.1 | Implementation of the Global Partnership on Disability Inclusion Pilot -HR components (detailed work plan separately) | [6 empty] | NO | RCO | To be done after consultation with RCO | TOR for consultant is finalized with coordinating RCO,LNOB and HRWG team | Recommendation: Outsource Company Services should provide training to outsource personnel ( Security, Cleaning , etc.) on DI - Suggested to the include in the Tor .
|  | 4.3 | Training for HR working group (need to identify) | 4.3.1 | Training to HR WG | Artificial Intelligence in HR HR Audit | 0 | 1 | 1000 | 2024-08-23 | 2024-08-01 | Simplified CBA | UNV | , UNDP, UN-Habitat, UN-Women to support | will initiate
[6 empty] | Total Budget for IAHRWG |  |  | 4000
| Status | Number of Activities | %
| Completed | 8 | 44.4444
| Ongoing | 7 | 38.8889
| Yet to be Initiated | 3 | 16.6667
|  | 18 | 100
Two Addtonal Work had been Completed ( participatin in Job fair organized by Government and Gendor Score Card)

## Member list
UN Nepal Common Services - Human Resource Working Group - Members 2025
S.N | Name | Designation | Agency | Email address | Contact number | Designation in working group (Chair/member/Alternate member)
1 | Durga Kumari Lohar | Admin/Finance Assistant | RCO | durga.kumari@un.org | 9841748276 | Member
2 | Sunita Pradhan | Administrative and Finance Officer | UN HABITAT | sunita.pradhan1@un.org | 9851001660 | Coordinator
3 | Lhawang Lama | Administrative Associate | UN-WOMEN | lhawang.lama@unwomen.org | 9849811843 | Deputy Coordinator
4 | Dhan Bahadur Shrestha | Admin/Finance Associate | FAO | Dhan.Shrestha@fao.org | 9802330506 | Member
5 | Bhakta Ram Baral | Admin. Specialist | FAO | Bhakta.baral@fao.org | 9802330519 | Alternate
6 | Rina Chhetri | HR Analyst | UNDP | rina.chhetri@undp.org | 981100780 | Member
7 | Ira Mishra | HR Associate | UNDP | ira.mishra@undp.org | 9851048813 | Alternate
8 | Marina Rai | Operations Officer | ILO | marina@ilo.org | 9851022729 | Member
9 | Deepika Chhetri | HR Officer | UNICEF | dechhetri@unicef.org | 9851107913 | Member
10 | Babita Das | HR Associate | UNICEF | bdas@unicef.org | 9851115780 | Alternate Member
11 | Arisha Gurung | HR Officer | UNICEF ROSA | argurung@unicef.org | 9802048253 | Member
12 | Glory Sodemba | HR Associate | UNICEF ROSA | gsodemba@unicef.org | 9802020914 | Alternate Member
13 | Gomba Sherpa | Associate (Nat Administrative Officer) | UNESCO | g.sherpa@unesco.org | 9851133591 | Member
14 | Richa Shrestha | Admin and Finance Assistant | UNESCO | r.shrestha@unesco.org | 9841592364 | Alternate Member
15 | Isha Dhaubhadel | HR Associate | UNFPA | dhaubhadel@unfpa.org | 9801056020 | Member
16 | Dhruba Aryal | HR Assistant | UNFPA | daryal@unfpa.org | 9801247913 | Alternate Member
17 | Dipesh Sherchan | Executive Associate (HR) | WHO | sherchand@who.int | 9801010111 | Member
18 | Ruby Bajracharya | HR Assistant | WHO | bajracharyar@who.int | 9860773833 | Alternate Member
19 | Mala Rai | HR Officer | WFP | mala.rai@wfp.org | 9851063911 | Member
20 | Sujan Pradhan | HR Associate | WFP | sujan.pradhan@wfp.org | 984904574 | Alternate Member
21 | Nandita RAI | HR Assistant | WFP | nandita.rai@wfp.org | 9851373881 | Alternate member
22 | Kamana Shrama Pandit | Admin Associate | UNHCR | sharmapk@unhcr.org | 9851235272 | Member
23 | Uma Basnet | Executive Support Associate | UNHCR | basnet@unhcr.org | 9851214371 | Alternate member
24 | Shrijana Maharjan | HR / Administration Senior Assistant | UNOPS | shrijanam@unops.org | 9801229443 | Member
25 | Rita Rana | HR Officer | IOM | rrana@iom.int | 9801004511 | Member
26 | Pishan Giri | HR Assistant | IOM | pgiri@iom.int | 9801148198 | Alternate member
27 | Aruna Shrsetha | Administrative Assistant | UNRCPD | aruna.shrestha@un.org | 9808467935 | Member
28 | Rina Pradhan | Programme Assistant | UNV | rina.pradhan@unv.org | 9851241260 | Alternate member
29 | Krishna Prasad Sedhain | Admin and Finance Associate | UNODC | krishna.sedhain@un.org | 9854045481 | Member

## Meeting Sheduel
Shedueld Meeting Date | Place
2024-01-23 | UN-Habitat
2024-02-20 | UN-Women
2024-03-19 | WFP
2024-04-23 | UNDP
2023-05-21 | ILO
2023-06-18 | WHO
2024-07-23 | FAO
2024-08-20 | UNICEF
2024-09-17 | UNESCO
2024-10-22 | IOM
2024-11-19 | UNFPA

## Driver Edu
S. No. | Name of Agency | Required Education | Experinace
1 | RCO | Secondary Education (SLC) | 3 years of experience for GS3 ( RCO has driver under only GS 3 )
2 | UN HABITAT | School leaving certificate (SLC) | School leaving certificate with 2 years of experience for GS2 and 3 years for GS3 .
3 | UN-WOMEN | School Leaving Certificate (SLC) | 3 years of experience for all level
4 | FAO | School Leaving Certificate (SLC) or Secondary Education Examination (SEE) | A minimum three years’ work experience as a driver in recognized and reputed organization with Flawless, safe driving record.
5 | UNDP | School leaving certificate (SLC) | School leaving certificate with 2 years of experience for GS2 / NPSA 2 and 3 years for GS3 / npsa.
6 | ILO | GS 2 and GS 3 Completion of secondary school education. Valid and clean driving licence | GS 2-A minimum of two years of relevant work experience with a safe driving record GS 3 Sr. Driver- A minimum of three years of relevant work experience with a safe driving record. Driving experience with a UN agency, diplomatic or international organization.
7 | UNICEF | Secondary School Education (SLC) | A minimum of two years of work experience as a driver in an international organization or UN system with a safe driving record is required.
8 | UNICEF ROSA | Secondary School Education (SLC) | A minimum of two years of work experience as a driver in an international organization or UN system with a safe driving record is required.
9 | UNESCO | Secondary School Education (SLC) | G1/G2 less than two year and for G3 minimum two years of work experience.
10 | UNFPA | Grade 8 pass (Special memo signed by HQ) | Min 2 years of experience for SLC pass and min 4 years of experience for grade 8 pass in an international organization, embassy or UN system with safe driving record
11 | WHO | Secondary School Education (SLC) | GS2:1 Year and GS3 - 2 years of experance
12 | WFP | Secondary School Education (SLC) | GS2: Two or more years of work experience as a Driver, preferably in an international organization, embassy or UN system.GS3: Three or more years of work experience as a Driver preferably in an international organization, embassy or UN system
13 | UNHCR | Completion of Primary education (grade 8) | 2 years relevant experience
14 | UNOPS | Secondary School Education (SLC) | two (2) years of relevant experience
15 | IOM | Secondary School Education (SLC) | 2 years relevant experience
16 | UNRCPD | School Leaving Certificate (SLC) | 2 years of experience for GS2 and 3 years for GS3
17 | UNV | No driver | N/A
18 | UNODC | Certificate – Secondary Education Examination -SLC | School leaving certificate with 2 years of experience for GS2 / NPSA 2 and 3 years for GS3 / NPSA.

## Summary of progress
UN Nepal Common Services - OMT work-plan 2024- Progreess as of 31 March 2024
S. No. | Output Categories | S.N for Activities | Activities | S.N for sub-activities | Sub- Activities | Indicators | Baseline data 2023 | Target | Cost USD | Timeline |  | CBA | Lead agency | Remarks | Progress as of 31October 2024
Inter Agency HR Working Group (IAHRWG)
1 | Benefit Administration | 1.1 | Benefit Management | 1.1.1 | UN DSA Survey-Regular DSA survey to keep the DSA rate up-to-date. | UN staff are compensate as per the prevailing market rates | 1 | 1 | 0 | 2024-01-01 | 2024-10-01 | NO |  | Activity supported by UN Habitat. To be consulted with Finance | HRWG supported to collect hotel list and FWG is working . Data Entry in the ICSC Protal
|  | 1.2 | Knowledge Sharing | 1.2.1 | Online General Information session to UN personnel on BOS by BOS team HQ | UN personnel sensitized on BOS | 0 | 1 | 0 | 2024-05-01 | 2024-05-01 | NO | ILO | Activity supported by UN Habitat
2 |  |  |  | 1.2.3 | Information on medical plan/services (CIGNA) | Enhance entitlement benefit awareness among staff. | 1 | 2 | 0 | January and March 2024 | Jan to June 2024 | NO | UNDP |  | UNDP organized Orientation on 18 on FTA /TA and 23 January 2024 to the personnel under NPSA/SC those are UNDP's administration .Facilitator was by Ms. Vanessa Vermeulen, CIGNA CIGNA Training provided to all FTA staff on 6 May and for SC on 3rd June
3 | Recruitment Services | 2.1 | Gender Parity | 2.1.1 | Conduct job fairs to raise awareness and attract female candidates considering GESI | Special measure put in place by agencies for achieving 50% women WD in UN Agencies as well as inclusion of Marginalized group .Ensure GESI guideline is followed by agencies | 2 | 1 | 2000 | 2024-07-01 | 2024-08-01 | NO | UNICEF | WHO, WFP, UNDP, UNV to support | Complted -Job Fair Conducted on 17 July 2024 at UN House , Pulchowk . 70 In persons Participants and 135 on-line Participants for Job Career session and 450 participants in Exhibition . Report with annexces shared to OMT Participated in Job Fair organized by Ministry of Labor, Employment and Security facilitated by FNCCI on 11th and 12th June 2024(UN Habitat, UNFPA, UNICEF, WFP, UNDP, IOM, ILO, UN Women, UNV, UNHCR, UNV)
4 |  |  |  | 2.1.2 | Maintain job Roster of female drivers /marginalized people | Roster of female driver created | 2 | 4 | 0 | 2024-12-01 | 2024-12-01 | NO | UN WOMEN | WFP/UNDP to support; Submit concept note incorporating best practices and challenges to OMT for further decision | Presented concept note with best practices to the OMT the Women on Wheel ( WFP /UNWOMEN) projects to OMT to initiate UN Joint activities as per the requested by OMT Concept note with cost was submitted to OMT (meeting conducted in WHO) and is still pending for OMT approval
5 |  |  |  | 2.1.3 | Establish GESI policy by agencies and policy Enhancement |  | 8 | 15 | 0 | 2024-12-01 | 2024-12-01 | NO | UNDP | UNHABITAT to support; GESI policy mapping survey on current status and report to OMT for further decision | UNDP hired consultant to finalize GESI policy. Mapping will be done within this year 2024
5 |  | 2.2 | Gender Equality and Social Inclusion in UN Workforce in Nepal. | 2.2.1 | 1. Quarterly basis GESI data presented to OMT and UNCT . 2. Conduct joint workshop with participation from HRWG, OMT, UNCT and LNOB WG on lesson learning and Way forward . | Number of agencies achieve above Gender Parity ; Lesson Learnt and action point developed; | 4 | 7 | 0 | Quarterly update | Quarterly update | NO | UN WOMEN | Survey, mapping, report and strategy; Implement in 2025 after endorsement by RC | Data as of 31 March 2024 and best Practices collected and compiled from all agencies. Best practives will be presented in the next OMT meeting
|  | 2.3 | Integrated Web-base Roster for Staff | 2.3.1 | Established web based roster for staff/personnel in DCO UN website | Reduce the lead time for recruitment process, save cost and fast track recruitment process. (number of CVs available in the webpage) | 46 | 75 | 0 | 2024-12-01 | 2024-12-01 | Simplified CBA | UNFPA |  | Completed
|  |  | UN Personnel Job security | 2.3.2 | Maintain roster of potential candidates in UN website to facilitate recruitment of personnel in the UN agencies | Number of UN personnel hired from the roster and number of UN personnel retained. | 0 | 5 | 0 | 2024-12-01 | 2024-12-01 |  | UNFPA |  | Some agencies are uploading profiles.
|  | 2.4 | Joint Recruitment Panel | 2.4.1 | Engage Staff members across UN agencies for various recruitment activities i.e. shortlisting , written test evaluation and interviews. | Cross utilization of expertise , recruitment of qualified personnel and cost saving by using internal resources. | 19 | 25 | 0 | Quarterly update | Quarterly update | NO | WFP |  | In progress
|  | 2.5 | Use Outsource company/consultant | 2.5.1 | Outsource company/consultant to be used for long listing and to conduct written tests in various recruitment process | Fast track recruitment process. Cost saving through the use of common agency in terms of human resource and time and efficient services. | 4 | 4 | 0 | 2024-12-01 | 2024-12-01 | LTA CBA | UNDP |  | UNDP, UN Habitat, WFP Reduced due to policies of individual agencies
6 |  | 2.6 | Harmonization in induction package. | 2.6.1 | Update and distribution of Common UN induction package to for all agencies | Updated induction package for all agencies | 1 | 1 | 0 | 2024-03-01 | 2024-03-01 | NO | UNICEF | Each agency will provide information by March in 2023 | Achieved
7 |  | 2.7 | Traineeship Programme for Socially Excluded Group | 2.7.1 | UN Nepal Joint Traineeship Programme to enhance capacity of socially excluded groups to join the UN workforce and others. Cohort X initiated | Increase number of participating agencies to promote the Programme and capacitate more people from marginalized groups. | 0 | 30 | 0 | 2024-03-01 | 2024-03-01 | NO | UNDP | Traineeship initiated in 2023; Will take forward in 2024; Tentatively onboard on March 2024 | 5 agencies ( UNDP, UNWOMEN, UNFPA and UNICEF) are participated . Only 34 trainees for Cohort X where as 9 agencies were in IX cohort with 65 Trainees. Survey has been done to map the know the effectiveness and way of expansion it
8 | Staff Wellbeing | 3.1 | PSEA - Prevention of Sexual Exploitation and Abuse and Sexual Harassment | 3.1.1 | Support for the PSEA Working Group in conducting the PSEA and SH induction or refresher sessions for all UN personnel, as well as adherence to the PSEA and SH standards of conduct. | Harassment and exploitation free environment among staff and office . Monitoring through monkey survey | 1 | 1 | 0 | 2024-12-31 | 2024-12-01 | NO | UN Habitat | UN-Women, RCO to support. Monkey survey report to be presented (Support to PSEA Coordinator as required); Baseline data will be provided later | Completed - Survey has been done and shared to OMT on 23 September 2024 .
9 |  |  |  | 3.1.2 | Include PSEA in the performance appraisal of the Agency PSEA Focal Points | PSEA is one of the priority areas of PSEA Focal in PMD or performance appraisal |  |  | 0 | 2024-12-01 | 2024-12-01 | NO | All Agencies
|  | 3.3 | UN care and UN day | 3.3.1 | Support UN Care activities for UN staff and dependents, including yearly celebration of UN Day. And update to HRWG on the UN care activities | Update on the UN care and UN day Activities to HRWG/OMT through of chair | 1 | 0 | 0 | May and June 2024 | May and June 2024 | NO | UNIC | After consultation with UN Care
4 | Training and Capacity Building | 4.1 | Follow up session on Disability Inclusion | 4.1.1 | Follow-up session on Disability Inclusive HR based on training of 2022 and implementation of joint actions and lessons identified in 2022. | Disability friendly environment and HR processes in the office | 0 | 1 | 1000 | 2024-04-01 | 2024-04-01 | NO | UN Habitat | RCO to be consulted ; Hire consultant to review action point taken by the agencies and further follow up session and report | will initiate
|  | 4.2 | Implementation of Disability Inclusion Pilot project | 4.2.1 | Implementation of the Global Partnership on Disability Inclusion Pilot -HR components (detailed work plan separately) | [6 empty] | NO | RCO | To be done after consultation with RCO
|  | 4.3 | Training for HR working group (need to identify) | 4.3.1 | Training to HR WG | Artificial Intelligence in HR | 0 | 1 | 1000 | 2024-08-23 | 2024-08-01 | Simplified CBA | UNV | , UNDP, UN-Habitat, UN-Women to support | will initiate
[6 empty] | Total Budget for IAHRWG |  |  | 4000

## Intervew Pannel
Used UN Internal Expert for Recuritmet Process -2023
S.N | Using Agency | Date | Post | Participating Agencies | Name | Time contribution | For
1 | UN-Habitat | Jan and Feb | MEAL Officer | UNDP | Dinesh Bista | 4 hrs | Questios preparation and Evaluation
|  |  |  | ILO | Kaji Babu Awale | 4 hrs | Questios preparation and Evaluation
|  | 2024-01-22 |  | UNDP | Purnima Bajracharay | 8 | Interview

## Work -Plan- 2022 (hidden)
UN Nepal Common Services - Human Resources Working Group - Workplan 2022
S. No. | Output Categories |  | Activities |  | Sub- Activities | Indicators | Baseline data 2021 | Target | Cost USD | Timeline | CBA | Leading Agencies | Status/Remarks' | Progress as of 19 July 2022 | Status as of 24 November 2022 | Under BOS as per 2021 WP ( Y/N) | Remarks | Planned Activities
1 | Benefit Administration | 1.1 | Benefit Management | 1.1.1 | UN DSA Survey-Regular DSA survey to keep the DSA rate up-to-date. | UN staff are compensate as per the prevailing market rates | 1 | 1 | 0 |  | NO | Finance Taskforce | Finance to initiate the process of DSA survey, HR working group to support where needed especially to collect the data from the field; compilation of the data | Reviewed the questioner form and suggested to consider reasonable accommodation questions for person with disability (LNOB) and security measure questions in the survey Form. HRWG had facilitated to get both with help of UN-Habitat and UNDSS. Similarly, HRWG facilitated to collect additional information from agencies. | Considered reasonable accommodation questions for person with disability (LNOB) and security measure questions in the survey Form as an Annexes. UNDSS will be part of member to review hotel security measure and recommendation on the basis of filled DSA survey form.- ON GOIN | Yes | Work in Progress. | DI & Security assessment checklist shared with experts
|  | 1.2 | Knowledge Sharing | 1.2.1 | Learning session to UN personnel on Agenda 2030 and the SDGs (Nepali and English) | Aware UN personnel on the UN core value in SDGs | 2 | 2 | 0 | 2022-12-01 | NO | RCO | All UN personnel-Virtual; to be facilitated by internal resource person (RCO)- 04 May 2022 Wedness day (11 AM to 12 AM) in English | All UN personnel-Virtual; to be facilitated by internal resource person (RCO)- by mid of August in English | Expert was not available. | YES |  | Sessions will be planned next year
|  | 1.3 | Knowledge Sharing | 1.3.1 | Sharing of information to staff on various benefits and entitlement ( UNJSPF or any) through Internal Expert - Online | Enhance entitlement benefit awareness among staff. | 1 | 1 | 0 | 2023-03-01 | NO | WHO/WFP | All UN personnel-Virtual; to be facilitated by internal resource person | 2 hours session for all staff to be planned - Aug 22. WFP to check with the UNJSPF colleague if they can hold another one for all staff or if record of the last session is available for viewing. | Last session was planned in 2021 for all UN staff from WFP international expert. For the year 2022 due to office priority of leading agencies for this activity the sessions was not planned | YES | Yet be done, this year it couldn't be done, we plan for 1st quarter next yr | Sessions will be planned next year
|  | 1.4 | Revised Remuneration for Consultancy Services | 1.4.1 | Remuneration Survey for Outsourced personnel | UN Consultant gets fees as per the prevailing market rates | 0 | 1 | 500 | 2022-03-01 | NO | UNDP | Most of the agencies are using 2015 common remuneration rate for consultancy services. Request for Concerned taskforce to take it as 2022 WP. HRWG will participated as per the requirement. | OMT decision ( 16 March 2022) is to use UNDP's 2019 consultancy rate as an reference . Hence, survey is not required this year | OMT decision ( 16 March 2022) is to use UNDP's 2019 consultancy rate as an reference . Hence, survey is not required this year. Request UNDP for sharing it | NO- New WP- DONE | No need to carry this year, UNDP recent consultant rates yet to be shared to all Agencies | To be planned for next year if we will not receive standard consultant rates of UNDP
2 | Recruitment Services | 2.1 | Gender Parity | 2.1.1 | Conduct job fairs to raise awareness and attract female candidates including GESI | Special measure put in place by agencies for achieving 50% women WD in UN Agencies as well as inclusion of Marginalized group .Ensure GESI guideline is followed by agencies | 0 | 1 | 500 | 2022-08-01 | NO | UNDP , UNICEF | Shifted from 2021 - Due to Covid-19 could not conducted it. As physical presence is required for job fair programmed in colleges and relevant places . Request to postponed it for next year | Conducted task force meeting including members from LNOB Team ( Maria, Rina, Deepika , Rabin, Sunita ) on 27 April 2022 to prepare action plan and way forwrad.Unicef to check with Bangladesh, UNICEF office about their experience to prepare action plan and way forward | As per the experinace from UNICEF Bangladesh , banners for the fair and circulate this advert in different INGO , UN and also in universities, Tragetting both professionals and students to join the fair - Organized job fair in the renowned hotel - HR worked with different sections to target those positions where it’s difficult to get qualified female candidates and then with the generic JDs They went ahead for generic Vacancy announcement | Yes | Work in Progress, challenge, integrate with UN day and UNV outreach program
|  |  |  | 2.1.2 | Maintain job Roster of female drivers /marginalized people |  | 0 | 10 to 15 | 0 | 2022-12-01 | NO | UN Women/WFP | Two agencies have reached out to many females but only 3 application was received and 2 of them were found suitable.- | Two agencies have reached out to many females but only 3 application was received and 2 of them were found suitable.- Orientation will be provided on programme to 2 candidates by April and- They are under training for languages and driving since May 2022 - one month The HRWG opines to run a joint recruitment process for Driver. A task force is created with following members to discuss further and come up with a plan: Lhawang Lama, Isha Dhaubhadel, Rina Chhetri, Babita Das, Srijana MAHARJAN. | Rachna Rasaily , WFP gave briefing on the Women on wheel ( Joint Project WFP and UNWOMEN ) and challenges to get Women Driver. She highlighted that Only 2 Women drivers selected. Now they are under training for English languages and heavy driving. Marina suggested to include the driving services under UN traineeship to promote it in UN Nepal , now they are in Roster , any agency can recruit them based on requirement. UNDP already hired 1 female driver from this roster. | YES | Achieved and Ongoing
|  |  |  | 2.1.3 | Establish GESI policy by agencies and policy Enhancement |  | 8 | 15 | 0 | 2022-12-01 | NO | UNDP | Policy has been reviewed by the consultant. The Action plan needs to be prepared to implement the policy recommendation | The policy revision is completed however, waiting for the final census data of population for update. | The policy revision is completed however, waiting for the final census data of population for update. | yes | Work in progress
|  | 2.2 | Gender Equality and Social Inclusion in UN Workforce in Nepal. | 2.2.1 | 1. Quarterly basis GESI data presented to OMT and UNCT . 2. Conduct joint workshop with participation from HRWG, OMT, UNCT and LNOB WG on lesson learning and Way forward . | Number of agencies achieve above Gender Parity ; Lesson Learnt and action point developed | 3 | 7 | 0 | 2022-12-01 | NO | UNWOMEN | HRWG group had meeting with Rabin Rai (member of LNOB WG) for further activities | HR focal point ( UNWOMEN) will present in next OMT meeting | UNWOMEN presented data as of 31 December 2021. 5 agencies namely RCO, UNWOMEN, UNESCO, UNICEF and UNICEF ROSA met the Gender Parity out of 21 Agencies | Yes | 1 session conducted for GESI score card from leaving no one behind HR lesson learnt session pending
|  | 2.3 | Integrated Web-based Roster for Staff | 2.3.1 | Established web based roster for staff/personnel in DCO UN website | Reduce the lead time for recruitment process, save cost and fast track recruitment process. | 0 | 50 | 0 | 2022-12-01 | Simplified CBA | UNFPA | at least 50 P11 uploaded by agencies | All agencies have agreed to add at least few candidates in the web roster by next OMT meeting | Web Page Established. Only few agencies are uploading CVs. More committment required from all agencies | Yes | Work in progress
|  |  | UN Personnel Job security | 2.3.2 | Maintain roster of potential candidates in UN website to facilitate recruitment of personnel in the UN agencies | Number of UN personnel hired from the roster and number of UN personnel retained. | 0 | 15 | 0 | 2022-12-01 |  | Each Agencies |  | UN-Habitat already hired one staff under SC from its own roster and under the process to hire one consultant form UNICEF roster. | UN-Habitat already hired one staff under SC from its own roster and under the process to hire one consultant form UNICEF roster.- | NEW WP for 2022 | Work in progress
|  | 2.4 | Joint Recruitment Panel | 2.4.1 | Engage Staff members across UN agencies for various recruitment activities i.e. shortlisting , written test evaluation and interviews. | Cross utilization of expertise , recruitment of qualified personnel and cost saving by using internal resources. | 11 | 25 | 0 | quarterly update | NO | WFP |  | UNDP, UNFPA are getting help from staff of other agency for the recruitment process. | UNDP, UNFPA, UNICEF are getting help from staff of other agency for the recruitment process. | Yes | Work in progress/Update from WFP awaiting
|  | 2.5 | Use Outsource company/consultant | 2.5.1 | Outsource company/consultant to be used for long listing and to conduct written tests in various recruitment process | Fast track recruitment process. Cost saving through the use of common agency in terms of human resource and time and efficient services. | 3 | 4 | 0 ( cost will be by using agencies) | XXXX | LTA CBA | UNDP | UNDP, WFP and UNFPA has been using | UNDP, WFP and UNFPA has been using | UNDP, WFP, UNFPA, UNICEF, UNOPS and UNHCR have been using | Yes | Work in progress
|  | 2.6 | Staff on board | 2.6.1 | Common UN induction package to be established for all agencies | Harmonization in induction package. | 10 | 1 | 0 | 2022-02-01 | NO | UNICEF | Incorporated suggestion provided by OMT members on First Draft . Awaiting few words of RC from RC0 to finalize the kit, which will be shared with OMT for final approval from UNCT once few words of RC incorporated. | It is edited by consultant as Aino , RCO advised . Fees funded by RCO. Aino has committed to share it at earliest possible as per yesterday mail ( 14 June) . Sending follow -up e-mail to her | Sunita requested to Aino (22/11/2022) to provide edited version of induction packg with Richard consent during the meeting at RC office. | Yes | Completed by HRTF/edited version with Aino
|  | 2.7 | Traineeship Programme for Socially Excluded Group | 2.7.1 | UN Nepal Joint Traineeship Programme to enhance capacity of socially excluded groups to join the UN workforce and others. Cohort IX initiated | Increase number of participating agencies to promote the Programme and capacitate more people from marginalized groups. | 64 | 64 | 0 | 2022-11-18 | NO | UNDP | The Cohort IX of Trainees were inducted on 20 December 2021 where around 43 trainees were taken up by 8 agencies. They have joined office since 3 January 2022. Currently their first evaluation is in process | The Cohort IX of Trainees were inducted on 20 December 2021 where around 43 trainees were taken up by 8 agencies. They have joined office since 3 January 2022. Currently their first evaluation is completed and shows positive outcome. They are also attending some trainings as per the plan. | The Cohort IX of Trainees were inducted on 20 December 2021 where around 47 trainees were taken up by 8 agencies. 42 trainees graduated on 14 Nov 2022 and 5 left for better job opportunities. | BOS | Completed cohort IX , graduation on 14 Nov 2022
|  | 2.8 | PSEA measures are in place to ensure UN personnel abide to PSEA standards | 2.8.1 | Implementation of the Safe Hiring Checklist with Sample Languages during hiring process for Preventing Sexual Exploitation and Abuse from the UN Personnel | Incorporated PSEA in the UN Personnel hiring process | 0 | 10 | 0 | Through out the year | NO | All Agencies | Tej Maya Dangol Presented guideline to the HRWG on 15 February 2022 . HR focal person will implement it once approved by UNCT through OMT ( Agencies may need get clearance from its HQ in few activities) | Tej Maya Dangol incorporated comments and Suggestions from HRWG and OMT. It is submitted to UNCT for final approval. Correct practices - Some agencies are using the PSEA questions during interview. Where as some are getting information during reference check. | Shared Safe Hiring Check list to OMT through Bernardo on 26 July 2022 and shares it to HRWG on 29 August 2022. |  | completed
3 | Staff Wellbeing | 3.1 | PSEA - Prevention of Sexual Exploitation and Abuse and Sexual Harassment | 3.1.1 | Support for the PSEA Working Group in conducting the PSEA and SH induction or refresher sessions for all UN personnel, as well as adherence to the PSEA and SH standards of conduct. | Harassment and exploitation free environment among staff and office . Monitoring through monkey survey | 0 | 10 | 0 | Through out the year | NO | UN Habitat, UN Women and RCO | HRWG coordinate with Tej ji for way forward | Tej Maya Dangol will share the template to collect information from Agencies on the practices of PSEAH orientations to personnel / partners/ vendors As Per Tej Ji orientation session will be conducted early August 2022 torugh town hall meeting | Two session conducted for PSEA focal point from june13 to 16 June 27 to 30 . J joint orientation session conducted September 2022 through town hall meeting. UNICEF conducted one session on capacity assessment of IPs with all agency PSEA focal point |  | Partially Completed
|  |  |  | 3.1.2 | Include PSEA in the performance appraisal of the Agency PSEA Focal Points | PSEA is one of the priority areas of PSEA Focal in PMD or performance appraisal | 0 | 10 | 0 | Through out the year | NO | UN Habitat, UN Women and RCO |  | Tej ji sent comprehensive roles of PSEA working group including PSEA Focal Points to UNCT for approval . RCO will circulate letter to HoA on the roles and responsibilities. After that PSEA working group will work on indicator for PSEA focal point performance evaluation | Richard UNRC, a.i has sent letter to HoA on 28 August 2022 to include PSEA focal point roles and responsibility in Performance Evaluation. Initial online meeting had been conducted between Tej ji and Sunita UN-Habitat to figure -out indicators. Second round meeting (Tej , Sunita and Sama) has been sheduled on 02 September 2022) . Indicator has been finalized in PSEA meeting in 15 September 2022 to share HRWG, OMT-UNCT for approval. - Indicator for peformance evaluation of PSEA focual point has been circulated in email to PSEA focal point and HRWG - It will be been sent to OMT for approval |  | Work in progress/yet to be approved by OMT
|  | 3.2 | Staff counselling services | 3.2.1 | Stress Management - Building Resilience to staff and dependance through expert | Well being of staff and dependents. End user survey to check quality of services. | 1 | 2 | 400 | 2022-08-01 | NO | IOM |  | Counseling - other facilitator also to be explored. Along with Counseling medical counseling on various topics including Post Covid care can also be organized for all staff. | Session on "Discovering self" By Pratima in September 2022 | yes | Complted
|  | 3.3 | UN care and UN day | 3.3.1 | Support UN Care activities for UN staff and dependents, including yearly celebration of UN Day. And update to HRWG on the UN care activities | Update on the UN care and UN day Activities to HRWG/OMT through of chair | 2 | 3 |  | Update in April , July and November 2022 UN care- UN day 1 time in a year | NO | UN-Habitat |  | Request to call to brief on UN care by Binda ji in next OMT meeting | Request Kala to bring Binda is to update | Yes | Complted
UN
4 | Training | 4.1 |  | 4.1.1 | Follow-up session on Disability Inclusive HR based on training of 2021 and identification of joint actions and lessons | Disability friendly environment and among the staff and office | 1 | 1 | 100 | 2022-04-01 |  | RCO | This will be done with coordination of RCO office | 8 activities has been identified with cost of USD 10,000.00 1. Consultant – USD 6,500.00 2. Workshop/Training and Logistic- USD 2,500 3. IEC material -USD 1,000.00 Kick-off meeting will be conducted through townhall meeting on 21 July 2022 Draft ToR ( Consultant hire) has been prepared, will be finalized by 22 July 2022. Planned to onboard consultant by Mid August 2022 through UNDP as FA issued to UNDP this process | Consultant has been on board from 01 September 2022 . - conducted 6 session for support staff in Nov 2022 - partciants XXXX - conducted 1 session each for HR and IT- 13 and 12 Participants - 1 session for procurement and Admin will be announced soon - 1 session for Hiring managers + HR on 30 Nov - 1 session for OMT on 25 Nov - 5000 USD allocated for reasonable accomodation for already hired 1 UNV (person with disability) | Yes | Work in progress
| Need to Identify |  |  | 4.1.2 | Implementation of the Global Partnership on Disability Inclusion Pilot -HR components (detailed work plan separately) | [6 empty] | RCO | Will follow once activities shared to HRWG
| Training | 4.2 | Staff Training | 4.1.3 | Strategic Human Resource Management | Enhanced HR Management capacity of HR Officials | 0 | 1 | 600 | 2022-05-01 | Simplified CBA | UNDP, UN-Habitat, UN-Women |  | The training to be planned in the week of August 2022. | Online training on “Strategic Human Resources Management” was held on 15 and 16 August 2022 ( 2 -half a day) to HRWG members (main and backup persons) Trainer was Reynaldo Calabdan, Thailand through Frontline service provider . There were 19 participants on day one 16 on day two. | Yes | Complted
[6 empty] | Total Cost |  |  | 2100